[image: image2.jpg]Sreenidhi Institute of Science and Tm:hnnlngy

AUTONOMOUS






Sreenidhi Institute of Science and Technology

(An Autonomous Institution)
Code No: 7K406 





                 
      Date: 28-Feb-2023 (FN)
B.Tech II-Year II- Semester External Examination, February/March-2023 (Supplementary)
CONSTRUCTION ENGINEERING AND MANAGEMENT (CIVIL)
Time:
 3 Hours







                    Max.Marks:70

 
Note:    a)  No additional answer sheets will be provided.

          

b)  All sub-parts of a question must be answered at one place only, otherwise it will not be valued.

          

c)  Missing data can be assumed suitably.





Bloom's Cognitive Levels of Learning (BCLL)

	Remember
	L1
	Apply
	L3
	Evaluate
	L5

	Understand
	L2
	Analyze
	L4
	Create
	L6









Part - A 



Max.Marks:20


[image: image1.wmf]Answer all QUESTIONS.
	
	
	BCLL
	CO(s)
	Marks

	1
	Define the following terms : Activity, Event, Dummy Activity, Optimistic Time.
	L1
	CO1
	[2M]

	2
	Define the following terms formwork and scaffolding
	L1
	CO2
	[2M]

	3
	Mention the hoisting equipments.
	L1
	CO3
	[2M]

	4
	What are the causes resource constraints?
	L2
	CO4
	[2M]

	5
	Define OSHA.
	L1
	CO5
	[2M]

	6
	What do you mean by deposits by the contractor?
	L2
	CO6
	[2M]

	7
	Write a short note on Time estimates in PERT network.
	L2
	CO1
	[2M]

	8
	What are the methods for transporting concrete?
	L2
	CO3
	[2M]

	9
	Write a note on Lean Construction.
	L2
	CO5
	[2M]

	10
	Mention the various equipments for excavation.
	L1
	CO2
	[2M]








           Part – B


   
 Max.Marks:50

ANSWER ANY FIVE QUESTIONS. EACH QUESTION CARRIES 10 MARKS.
	
	 
	
	BCLL
	CO(s)
	Marks

	11.
	a)
	Describe in detail stages of construction planning.
	L2
	CO1
	[5M]

	
	b)
	A project schedule has the following characteristics as shown in Table, Calculate these.

i)  Construct PERT network and determine the expected project completion time.

ii) Compute TE and TL for each activity. 

Activity

Immediate Predecessors

Optimistic duration

Normal Duration

Pessimistic Duration

A

None

2

3

4

B

None

2

3

4

C

B

6

7

8

D

A

5

6

7

E

A

4

5

6

F

C,D

4

8

12

G

C,D

4

5

6

H

G

2

3

4

I

E,G

2

4

6


	L3
	CO1
	[5M]

	
	
	
	
	
	

	12.
	a)
	How would you compare the types of foundations?
	L3
	CO2
	[5M]

	
	b)
	Mention the merits and demerits of precast concrete construction.
	L2
	CO2
	[5M]

	
	
	
	
	
	

	13.
	a)
	How would you compare conventional construction methods Vs mechanized methods?
	L3
	CO3
	[5M]

	
	b)
	Briefly explain the various equipment for transportation of materials.
	L2
	CO3
	[5M]

	
	
	
	
	
	

	14.
	a)
	Elaborate following terms Resource Leveling, Resource Smoothing.
	L2
	CO4
	[5M]

	
	b)
	Write a short note on Line of balance technique and Earned value management.
	L2
	CO4
	[5M]

	
	
	
	
	
	

	15.
	a)
	Briefly explain the causes and cost of accidents.
	L2
	CO5
	[5M]

	
	b)
	Write a short note on Building Information Modeling (BIM) in project management.
	L2
	CO5
	[5M]

	
	
	
	
	
	

	16.
	a)
	Write a short note on termination of contract and conditions of contract.
	L2
	CO6
	[5M]

	
	b)
	Discuss about Delays and penalties in contract management.
	L3
	CO6
	[5M]

	
	
	
	
	
	

	17.
	a)
	Differentiate between PERT and CPM networks.
	L2
	CO1
	[4M]

	
	b)
	What are the disadvantages of slip form construction?
	L2
	CO2
	[3M]

	
	c)
	Write a short note on back hoe loader and dozer.
	L2
	CO3
	[3M]

	
	
	
	
	
	

	18.
	a)
	Define scheduling. Mention the advantages of scheduling.
	L2
	CO4
	[4M]

	
	b)
	Mention the preventive measure the in construction industry.
	L2
	CO5
	[3M]

	
	c)
	Enumerate the various advantages of arbitration.
	L2
	CO6
	[3M]


-- 00 -- 00 –
H.T No





Regulations:


A18











PAGE  
Page 1 of 2

_1604898669.unknown

